Fly GACA

Academy Onboarding Playbook

Contract Signature to 60-Day Pilot Review

Fly GACA · Customer Success · v1.0 · May 2026

Captain Adel Yahya A. Madkhali, GACA-Licensed Pilot & Founder

i@flygaca.com  ·  support@flygaca.com  ·  +966 51 096 6969

Why this matters: Structured onboarding is the single biggest lever for pilot-to-contract conversion. Every academy that completes a proper Day 0 kickoff converts at 3x the rate of those that skip it.

1. Pre-Kickoff (Day -5 to Day 0)

The five days before kickoff set the technical and relational foundation. Incomplete setup on Day 0 is the leading cause of slow cadet activation.

1.1 Contract & Commercial

•  Signed academy contract received and countersigned by Captain Adel

•  Invoice issued and initial payment confirmed (or PO received)

•  School code generated in admin panel (format: ACAD-[ISO country]-[3-letter abbrev]-[year])

•  Academy added to CRM with tier, cadet count, and renewal date fields populated

1.2 Technical Setup

•  Bulk roster import template sent to academy coordinator (CSV: first name, last name, email, student ID, cohort)

•  Roster received and validated -- missing fields flagged within 24 hours

•  Cadet accounts provisioned; welcome emails queued

•  Instructor accounts created (minimum 1 per 30 cadets)

•  Academy branding assets collected (logo PNG, primary color hex) and applied to academy subdomain

•  Data import confirmed: any prior exam scores migrated if applicable

1.3 Kickoff Call Scheduling

•  30-minute video call scheduled via calendar link

•  Attendees: CS Manager (Fly GACA), academy coordinator, lead instructor, IT contact

•  Pre-read deck sent 48 hours before: product overview, success metrics, 60-day timeline

2. Day 0 -- Kickoff Call

2.1 Call Agenda (30 minutes)

| Time | Topic | Owner |
| --- | --- | --- |
| 0:00-0:05 | Intros & housekeeping | CS Manager |
| 0:05-0:12 | Platform walkthrough -- cadet view + instructor dashboard | CS Manager |
| 0:12-0:18 | 60-day pilot goals & KPI targets | CS Manager + Coordinator |
| 0:18-0:25 | Q&A, escalation path, WhatsApp group created | All |
| 0:25-0:30 | Next check-in booked (Day 7) | CS Manager |

2.2 Day 0 Deliverables (CS Manager sends within 2 hours)

•  Meeting notes + action items with owners and due dates

•  Welcome email sent to all cadets from support@flygaca.com

•  WhatsApp Business group created: [Academy Name] x Fly GACA CS

•  Instructor quick-start PDF shared

3. Week 1 -- Activation Sprint

Why this matters: 80% cadet activation within 7 days is the leading indicator of a successful pilot. Monitor daily and intervene if activation stalls below 50% by Day 4.

3.1 Cadet Activation Tracking

•  Dashboard checked daily: % of cadets who have logged in at least once

•  Target: 80% or more by Day 7

•  Day 3 intervention: if less than 40% activated, CS Manager contacts coordinator with re-send instructions

•  'First question asked' milestone -- tracked per cadet; celebrated in WhatsApp group

3.2 Instructor Dashboard Tour (async)

•  5-minute Loom video sent: how to view cadet progress, questions asked, exam attempts

•  Instructor invited to book optional 1:1 screen-share if needed

3.3 Day 7 Check-in (15 minutes)

•  Review activation rate vs. 80% target

•  Identify any technical blockers (login issues, content gaps)

•  Confirm WhatsApp group is active and coordinator is responsive

4. Week 2-4 -- Engagement Cadence

4.1 Weekly Check-in (15 minutes, every Tuesday)

•  Activation rate, questions/cadet/week, exam attempts

•  Any support tickets open >48 hours

•  Feature spotlight (one new capability highlighted per week)

4.2 Weekly Digest Email (automated, every Monday)

•  Top 5 most-asked questions that week

•  Cadet leaderboard (optional, academy can enable/disable)

•  Tip of the week -- pulled from GACA library

4.3 Monthly Newsletter

•  Product updates and new GACA documents added to library

•  Academy aggregate stats (questions asked, exam pass rate trend)

•  Aviation regulatory news relevant to KSA cadets

5. Day 30 -- Mid-Pilot Review

5.1 KPI Report

| KPI | Target | Status |
| --- | --- | --- |
| Cadet activation rate | >=80% |  |
| Questions/cadet/week | >=2 |  |
| Instructor logins/week | >=2 |  |
| Exam attempts/cadet | >=1 |  |
| NPS (instructor survey) | >=30 |  |

5.2 Mid-Pilot NPS

•  Survey sent to all instructors (not cadets at this stage)

•  2-question: 0-10 NPS + 'What is one thing we could improve?'

•  Detractors (0-6): CS Manager calls within 48 hours

•  Passives (7-8): CS Manager sends improvement roadmap

•  Promoters (9-10): Request testimonial quote for case study

6. Day 55 -- Pre-Conversion Preparation

6.1 Full Pilot Results Pack

•  Cadet activation achieved vs. target

•  Total questions asked through Captain Adel AI

•  Top 5 GACA documents accessed

•  Exam attempt rate and pass rate improvement (if baseline exists)

•  Instructor satisfaction (NPS from Day 30 survey)

6.2 ROI Calculation Template

| Metric | Baseline (Pre-Fly GACA) | Pilot Result | Delta |
| --- | --- | --- | --- |
| Instructor hours answering cadet questions/week | X hrs | Y hrs | Delta hrs saved |
| GACA exam first-attempt pass rate | X% | Y% | +Z pts |
| Cost per cadet of study materials | SAR X | SAR 150/yr | SAR Delta |
| Cadet satisfaction (if measured) | -- | NPS Y | -- |

6.3 Renewal Proposal

•  Annual contract at 150 SAR/cadet/year sent via DocuSign

•  5% loyalty discount if signed by Day 60

•  Upsell options: additional instructor seats, branded content modules

7. Day 60 -- Conversion or Wrap-Up

7.1 Conversion

•  Contract signed -- transition to ongoing CS rhythm (see Section 8)

•  Invoice issued within 24 hours

•  School code upgraded from 'Pilot' to 'Active' status

7.2 Non-Conversion

•  Exit interview scheduled (15 minutes): primary reason for not converting

•  Reason logged in CRM with theme tag (price / product / timing / internal budget)

•  30-day and 90-day re-engagement emails queued

•  Feedback routed to product roadmap log

8. Hand-Off to Ongoing CS Rhythm

8.1 Quarterly Business Review (QBR) Cadence

•  QBR scheduled at Q1, Q2, Q3, Q4 (60-minute video call)

•  Agenda: usage review, product roadmap preview, renewal/expansion discussion

8.2 Health Score Monitoring

•  Academy health score calculated weekly (see Customer Health Score Framework, FG-CS-005)

•  Amber band (40-69): CS Manager proactive outreach within 5 business days

•  Red band (0-39): Founder save call scheduled within 5 days

8.3 Annual Renewal Cycle

•  Renewal process starts 90 days before expiry (see Renewal & Churn Reduction Playbook, FG-CS-006)

Document reference: FG-CS-001  |  Owner: CS Manager  |  Review: Quarterly