## Cover
Fly GACA — Digital Office Setup Progress Tracker
v1.0 · May 2026 · Captain Adel · 14-day setup plan
How to use this tracker
Sheet 'Master Tasks' | Day-by-day setup tasks. Update Status column as you go (Not started / In progress / Done / Blocked).
Sheet 'Tool Subscriptions' | Every recurring SaaS subscription. Track billing date, monthly cost, renewal.
Sheet 'Email Aliases' | Each @flygaca.com alias. Mark Setup Status when MX/forward is configured + tested.
Sheet 'Calendar Holds' | Recurring meetings to put on the founder calendar. Tick when added.
Sheet 'Done Criteria' | Definition-of-done for declaring 'digital office complete.' All items must be checked.
Recurring monthly cost (founder stage) | ≈ SAR 500-600/month. See Tooling Stack Selection doc for breakdown.
Total founder time | 1-2 working days of active work + ~1 week of async waits (DNS, vendor approvals).

## Master Tasks
Master Setup Tasks
Day | Phase | Task | Owner | Status | Cost (SAR/mo) | Notes
Day 1 | 1 - Domain & Email | Move flygaca.com DNS to Cloudflare (free) | Founder | Not started | 0 | Free tier
Day 1 | 1 - Domain & Email | Sign up Google Workspace Business Starter, verify domain | Founder | Not started | 25 | 1 user
Day 1 | 1 - Domain & Email | Configure MX records, wait for propagation | Founder | Not started | 0 | 30 min wait
Day 1 | 1 - Domain & Email | Create i@flygaca.com primary, MFA + recovery code | Founder | Not started | 0 | Hardware key recommended
Day 1 | 1 - Domain & Email | Configure all email aliases (see Email Aliases sheet) | Founder | Not started | 0 | Routes all to founder until hires
Day 1 | 1 - Domain & Email | Set up SPF + DKIM + DMARC records | Founder | Not started | 0 | Anti-spoofing
Day 1 | 1 - Domain & Email | Set up Google Drive shared drive 'Fly GACA' with folder structure | Founder | Not started | 0 | Mirror Office Paperwork tree
Day 1 | 1 - Domain & Email | Upload Investor Package + Office Paperwork to Drive | Founder | Not started | 0 | Bulk upload
Day 2 | 1 - Domain & Email | Configure Google Calendar founder time blocks | Founder | Not started | 0 | See Operating Rhythm doc
Day 2 | 1 - Domain & Email | Configure Gmail signature for i@ + sales@ | Founder | Not started | 0 | Brand asset kit dependency
Day 2 | 1 - Domain & Email | Install Drive desktop client, selective sync | Founder | Not started | 0
Day 3 | 2 - Knowledge & Comms | Create Notion workspace, Plus plan | Founder | Not started | 38 | 1 user
Day 3 | 2 - Knowledge & Comms | Mirror Office Paperwork tree as Notion pages | Founder | Not started | 0 | Top-level only
Day 3 | 2 - Knowledge & Comms | Migrate Decision Log + Risk Register + Sub-Processor List + Vendor Register to Notion DBs | Founder | Not started | 0 | Operational benefits
Day 3 | 2 - Knowledge & Comms | Captain Adel persona Notion page (source of truth) | Founder | Not started | 0
Day 4 | 2 - Knowledge & Comms | Create Slack workspace flygaca.slack.com (free) | Founder | Not started | 0 | Free tier
Day 4 | 2 - Knowledge & Comms | Configure channels per Slack Blueprint | Founder | Not started | 0 | 10 public + 5 private
Day 4 | 2 - Knowledge & Comms | Connect Drive + Notion + Calendar bots to Slack | Founder | Not started | 0
Day 4 | 2 - Knowledge & Comms | Set up daily standup reminder bot in #standup at 10am KSA | Founder | Not started | 0
Day 5 | 2 - Knowledge & Comms | Create GitHub organization 'flygaca', migrate repository | Founder | Not started | 20 | Team plan
Day 5 | 2 - Knowledge & Comms | Branch protection on main; connect GitHub to Slack | Founder | Not started | 0
Day 5 | 2 - Knowledge & Comms | VS Code or Cursor as founder daily editor | Founder | Not started | 0 | Free / personal pref
Day 6 | 3 - Pipeline & Ops | Create HubSpot account (free tier) | Founder | Not started | 0 | Up to 1M contacts
Day 6 | 3 - Pipeline & Ops | Configure 2 pipelines: Academy Sales + Investor Outreach | Founder | Not started | 0 | See HubSpot CRM Config doc
Day 6 | 3 - Pipeline & Ops | Import Saudi Investor Target List as contacts + create deals | Founder | Not started | 0 | Bulk CSV import
Day 6 | 3 - Pipeline & Ops | Connect Gmail + Calendar to HubSpot | Founder | Not started | 0 | Auto-log emails
Day 7 | 3 - Pipeline & Ops | Sign up Calendly Standard, connect Google Calendar | Founder | Not started | 38 | Founder only
Day 7 | 3 - Pipeline & Ops | Create 3 booking links: 30-min academy demo, 30-min investor first-meeting, 60-min advisor | Founder | Not started | 0
Day 7 | 3 - Pipeline & Ops | Add booking links to Gmail signature, LinkedIn, X bios | Founder | Not started | 0
Day 8 | 3 - Pipeline & Ops | Sign up Linear (free under 10 users) | Founder | Not started | 0 | Free tier
Day 8 | 3 - Pipeline & Ops | Configure 3 cycles: Product, Content, Ops; migrate GitHub Issues | Founder | Not started | 0
Day 8 | 3 - Pipeline & Ops | Connect Linear to Slack and GitHub | Founder | Not started | 0
Day 9 | 3 - Pipeline & Ops | Sign up 1Password Teams (flat SAR 75/mo for first 10) | Founder | Not started | 75 | Predictable cost
Day 9 | 3 - Pipeline & Ops | Create vaults + migrate every credential from browser | Founder | Not started | 0 | Day of cleanup
Day 9 | 3 - Pipeline & Ops | Order + register YubiKey hardware key for primary Google | Founder | Not started | 0 | One-time ~SAR 200
Day 10 | 3 - Pipeline & Ops | Open SME corporate bank account (Al Rajhi or SNB) | Founder | Not started | 0 | Requires CR — may be in flight
Day 10 | 3 - Pipeline & Ops | Sign up Zoho Books (Saudi-friendly, ZATCA-ready) | Founder | Not started | 75 | Standard plan
Day 10 | 3 - Pipeline & Ops | Connect bank + Moyasar to Zoho Books | Founder | Not started | 0 | Auto-reconciliation
Day 11 | 4 - Tracking & Auto | Set up Google Analytics 4 + Plausible on flygaca.com | Founder | Not started | 75 | Plausible privacy-friendly
Day 11 | 4 - Tracking & Auto | Configure conversion events: signup, trial start, trial-to-paid, academy form | Founder | Not started | 0
Day 11 | 4 - Tracking & Auto | Build founder one-page dashboard in Plausible/Looker Studio | Founder | Not started | 0
Day 12 | 4 - Tracking & Auto | Sign up Sentry (free Developer tier) | Founder | Not started | 0 | Free tier ample
Day 12 | 4 - Tracking & Auto | Wire Sentry into Captain Adel chat function + SPA | Founder | Not started | 0
Day 12 | 4 - Tracking & Auto | Configure alerts: Sev1 → SMS founder + Slack #incidents | Founder | Not started | 0 | Twilio + Zapier
Day 13 | 4 - Tracking & Auto | Sign up Loom Business plan | Founder | Not started | 56 | Async demos
Day 13 | 4 - Tracking & Auto | Sign up Figma Free | Founder | Not started | 0 | Solo tier
Day 14 | 4 - Tracking & Auto | Sign up Zapier Starter | Founder | Not started | 75 | Cross-tool automation
Day 14 | 4 - Tracking & Auto | Initial Zaps: HubSpot deal won → Slack + Drive folder; Gmail label investor → HubSpot log | Founder | Not started | 0
Day 14 | 4 - Tracking & Auto | Configure backup: Drive → Cloudflare R2 weekly encrypted | Founder | Not started | 20 | Pay-as-you-go
Day 14 | 4 - Tracking & Auto | Final review: every credential in 1Password, every alias resolving, every recurring meeting on calendar | Founder | Not started | 0 | Definition of done — see Done Criteria sheet

## Tool Subscriptions
Tool Subscriptions Tracker
Tool | Plan | Cost SAR/mo | Billed | Next renewal | Owner | Status | Notes
Google Workspace | Business Starter (1 user) | 25 | Annual | 2027-05 | Founder | Pending | Email/Drive/Calendar/Meet
Notion | Plus (1 user) | 38 | Annual | 2027-05 | Founder | Pending | Knowledge wiki
Slack | Free | 0 | — | — | Founder | Pending | Free tier; upgrade Pro at 5+ users
HubSpot CRM | Free | 0 | — | — | Founder | Pending | Up to 1M contacts free
Calendly | Standard | 38 | Annual | 2027-05 | Founder | Pending | Booking links
Linear | Free (<10 users) | 0 | — | — | Founder | Pending | Free under 10 users
1Password | Teams flat | 75 | Monthly | Recurring | Founder | Pending | Flat fee covers 10 users
GitHub | Team | 20 | Monthly | Recurring | Founder | Pending | Private repos + branch protection
Zoho Books | Standard | 75 | Annual | 2027-05 | Founder | Pending | Saudi-friendly, ZATCA-ready
Sentry | Developer (free) | 0 | — | — | Founder | Pending | Free tier ample
Plausible Analytics | Growth (10K pageviews) | 75 | Monthly | Recurring | Founder | Pending | Privacy-friendly
Loom | Business | 56 | Monthly | Recurring | Founder | Pending | Async demos
Figma | Free (solo) | 0 | — | — | Founder | Pending | Solo tier
Zapier | Starter | 75 | Monthly | Recurring | Founder | Pending | Cross-tool automation
Cloudflare DNS | Free | 0 | — | — | Founder | Pending | Free tier
Cloudflare R2 (backup) | Pay-as-you-go | 20 | Monthly | Recurring | Founder | Pending | Drive backup ~5GB
Twilio (SMS alerts) | Pay-as-you-go | 50 | Monthly | Recurring | Founder | Pending | SAR 50/mo cap
TOTAL |  | 547 |  |  |  |  | ≈ USD 146/mo

## Email Aliases
Email Aliases — Setup Tracker
Alias | Routes to (Day 1) | Filter / Label | Auto-responder | MX Setup Status | Tested | Notes
i@flygaca.com | Founder primary | Personal — no filter | No | Pending | No | Personal + advisors
captain@flygaca.com | Founder | Captain Adel | No | Pending | No | Persona + community
sales@flygaca.com | Founder | Sales / yellow star | No | Pending | No | Academy + individual inbound
support@flygaca.com | Founder → CSM month 6 | Support / red star urgent | No | Pending | No | Customer support
press@flygaca.com | Founder | Press / mobile push | No | Pending | No | Media inquiries
privacy@flygaca.com | Founder/DPO | Privacy/PDPL / red star | No | Pending | No | PDPL data subject requests · 30-day SLA
legal@flygaca.com | Founder → counsel | Legal | No | Pending | No | External counsel routing
billing@flygaca.com | Founder → finance | Billing | No | Pending | No | Payment + invoices
careers@flygaca.com | Founder | Careers low-priority | Yes (acknowledgment) | Pending | No | Job applications
feedback@flygaca.com | Founder | Feedback | No | Pending | No | Captain Adel + product feedback
investors@flygaca.com | Founder only | Investors / never archive | No | Pending | No | Add to HubSpot via Zapier
partnerships@flygaca.com | Founder | Partnerships | No | Pending | No | BD inbound
security@flygaca.com | Founder/CISO | Security / red star | No | Pending | No | Vulnerability disclosures
verify@flygaca.com | Automated | — | Yes (full auto) | Pending | No | Cert + credential verification
noreply@flygaca.com | Automated only | — | Yes (bounce) | Pending | No | Transactional outbound

## Calendar Holds
Recurring Calendar Holds — Setup Tracker
Cadence | Meeting / Hold | Day & Time (KSA) | Duration | Set up Y/N | Notes
Daily | Async standup post in #standup | Sun-Thu 10am | — | No | Slack reminder bot
Daily | Deep work block #1 (protected) | Sun-Thu 9am-11am | 2 hr | No | Auto-decline meetings
Daily | Customer call slot 1 | Sun-Thu 11am-12pm | 1 hr | No | Calendly-bookable
Daily | Deep work block #2 (protected) | Sun-Thu 2pm-4pm | 2 hr | No | Auto-decline meetings
Daily | Inbox closeout + tomorrow plan | Sun-Thu 5:30pm-6:30pm | 1 hr | No
Weekly | Founder ↔ direct report 1:1 (per hire) | Monday 9am-12pm (block) | 30 min each | No | Activate as team grows
Weekly | Sales pipeline review | Sunday 9am-9:30am | 30 min | No | Async-first
Weekly | Captain Adel content review | Tuesday 2pm-3pm | 1 hr | No | With editor once hired
Weekly | Weekly retrospective + plan next | Thursday 5pm-5:30pm | 30 min | No | Solo, with notebook
Bi-weekly | Founder + Advisor #1 call | Wed 10am-11am (alternating) | 1 hr | No | Once advisor signed
Bi-weekly | Founder + Advisor #2 call | Wed 10am-11am (alternating) | 1 hr | No | Once advisor signed
Monthly | All-Hands meeting | 1st Sunday 11am | 1 hr | No | Even if solo, run the rhythm
Monthly | Investor update sent | 5th of each month (reminder) | 30 min prep | No | Email send, not a meeting
Monthly | Board pack prep + review | Last Thursday 4pm | 1.5 hr | No | Self-review until board exists
Monthly | Risk Register update | Last Thursday 6pm | 30 min | No
Quarterly | OKR + QBR session | End of quarter 9am | 3 hr | No | Strategic deep-dive
Quarterly | Pre-mortem refresh | End of quarter 1pm | 1.5 hr | No | Revisit failure modes
Quarterly | Founder Time Audit | End of quarter 4pm | 1 hr | No | Review last quarter's calendar
Quarterly | Compensation + bands review | End of Q4 | 1.5 hr | No | Annual pay refresh
Quarterly | Vendor review | End of Q4 | 1 hr | No | Critical vendors only
Annually | Strategy offsite | December | 1-2 days | No | Off-site location
Annually | Financial model rebuild | December | 1 day | No | 8 hr block
Annually | PDPL audit with counsel | December | 1 day | No | External counsel-led
Annually | Brand voice + content strategy refresh | December | 1 day | No
Annually | Team retreat (when team > 5) | Q1 of new year | 3-5 days | No | Future

## Done Criteria
Definition-of-Done — Digital Office Complete
Criterion | Done Y/N | Verification
Send a test email from i@flygaca.com — receives, replies, formats correctly | No | Self-test
Send a test email to verify@flygaca.com — auto-reply fires within 1 minute | No | Self-test
Send a test email to support@flygaca.com — labels correctly, founder receives push | No | Self-test
Open Drive on a fresh device with i@ login — entire structure visible per permissions | No | Test device
Open Notion on a fresh device with i@ login — workspace accessible | No | Test device
Slack #general loads with all bot integrations live | No | Visual check
Slack daily standup reminder fires at 10am KSA | No | Wait + observe
HubSpot shows imported Saudi Investor Target List as contacts + deals | No | CRM visual check
Calendly booking link tested — successfully books a slot, sends Google Meet invite | No | Self-test
1Password contains every credential; no credentials remain in browser/scratch | No | Browser audit
Google Calendar shows: founder time blocks + recurring all-hands + monthly investor update reminder | No | Visual check
Plausible Analytics shows real traffic from flygaca.com | No | Pageview test
Sentry receives a test error from the SPA | No | Trigger test error
Loom can record + share a 1-min demo successfully | No | Self-test
Zapier: HubSpot deal won → Slack #wins post fires correctly | No | Test deal
Drive backup to Cloudflare R2 confirmed via first weekly run | No | Wait 7 days, verify
Sub-Processor List + DPA Register doc updated with: Google, HubSpot, Zoho, Notion, Slack, Linear, 1Password, Sentry, Plausible, Loom, Figma, Zapier, Cloudflare | No | Doc update
Founder can find any document via Drive search OR Notion search in <30 seconds | No | Stopwatch test
All recurring meetings on calendar with auto-decline outside founder availability | No | Calendar review
Founder posts first standup, first investor update, first content piece — all using new infrastructure | No | First-week tour