## Risk Register
Risk ID | Category | Description | Likelihood (1–5) | Impact (1–5) | Inherent Score (LxI) | Current Mitigations | Residual Likelihood | Residual Impact | Residual Score | Owner | Status | Last Reviewed | Next Review
RR-001 | Strategic | Vision 2030 aviation sector investment slows or pivots, reducing academy modernisation budgets and TAM for EdTech spend | 3 | 4 | 12 | Monitor GACA capital announcements quarterly; diversify to private academy chains not solely dependent on government funding; maintain lean burn to extend runway through cycle | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-002 | Regulatory | GACA withdraws non-objection or declines to endorse Captain Adel, blocking academy adoption | 2 | 5 | 10 | Maintain all GACA citations linked to official sources; add prominent 'study aid only' disclaimers; seek early informal GACA engagement; never brand as 'GACA-approved' | 2 | 4 | 8 | Founder | Open | May 2026 | May 2027
RR-003 | Financial | Gemini API unit cost spikes materially (>50%) as Google reprices Vertex AI, compressing gross margin below 70% | 3 | 3 | 9 | Monitor Google pricing announcements; design prompt caching layer to reduce token spend; benchmark alternative models (Claude, GPT-4o) quarterly; include API cost cap in financial model | 2 | 2 | 4 | Founder | Open | May 2026 | May 2027
RR-004 | Operational | Moyasar payment gateway experiences prolonged outage, blocking academy invoice collection and cadet subscription renewals | 2 | 4 | 8 | BCP/DR Section 4.2 activated; queue retry logic; maintain 30-day AR buffer; evaluate HyperPay as backup processor | 1 | 3 | 3 | Founder | Monitoring | May 2026 | May 2027
RR-005 | Strategic | Founder (Captain Adel Yahya A. Madkhali) is incapacitated, creating single-point-of-failure in product, sales, and regulatory relationships | 2 | 5 | 10 | Key-person life insurance ≥3M SAR (pending); onboard first technical hire with documented system access; record all GACA relationship contacts; BCP/DR Section 4.4 | 2 | 4 | 8 | Founder | Open | May 2026 | May 2027
RR-006 | Reputational | Captain Adel AI produces hallucinated answer citing non-existent GACA regulation; cadet relies on it for exam or real flight operation | 3 | 5 | 15 | RAG eval pass rate KR (≥85% target); every answer requires citation; BM25 retrieval grounds answers; disclaimer on every session; instructor NPS tracking flags quality drops | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-007 | Strategic | Well-funded foreign EdTech incumbent (e.g. Jeppesen, CFI Notebook) localises product for KSA market and undercuts on price | 2 | 4 | 8 | Build deep GACA-citation moat not replicable without KSA regulatory relationships; sign academies on multi-year cohort contracts; leverage Arabic-first and in-Kingdom data residency as differentiators | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-008 | Operational | Academy procurement cycle exceeds 12 months due to internal bureaucracy, budget cycles, or committee approvals, delaying ARR ramp | 4 | 3 | 12 | Map procurement process in discovery call; identify internal champion; offer 60-day free pilot to bypass procurement; target private academies first (shorter cycles); track stage-duration in CRM | 3 | 2 | 6 | Founder | Open | May 2026 | May 2027
RR-009 | Regulatory | Commercial Registration (CR) delayed beyond Q3 2026, preventing revenue collection and formal contracts with academies | 3 | 4 | 12 | Engage Balady/MISA agent; track application weekly; use pilot LOI structure pending CR; legal counsel on interim contracting options | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-010 | Regulatory | PDPL audit or enforcement action by NDMO due to sub-processor data residency gap or DPA non-compliance | 2 | 4 | 8 | All data in me-central2 KSA; DPA executed with all active sub-processors; Sub-Processor Register maintained; annual PDPL compliance review; legal counsel on retainer | 1 | 3 | 3 | Founder | Monitoring | May 2026 | May 2027
RR-011 | Regulatory | ZATCA Fatoora Phase 2 e-invoicing deadline missed, resulting in penalty and inability to issue compliant invoices to academies | 2 | 4 | 8 | Moyasar Fatoora integration confirmed; accounting firm on Fatoora compliance retainer; track ZATCA deadline calendar; test invoice flow before first commercial contract | 1 | 3 | 3 | Founder | Monitoring | May 2026 | May 2027
RR-012 | Financial | Bridge round (3M SAR) not closed, leaving <6 months runway before first revenue | 2 | 5 | 10 | Term sheet in progress; bridge structured with SAFE/convertible note; reduce burn to minimum viable; personal founder capital as backstop; Series A pipeline parallel-tracked | 2 | 4 | 8 | Founder | Open | May 2026 | May 2027
RR-013 | Cyber | Firebase Authentication misconfiguration or credential leak exposes cadet personal data (email, phone, study history) | 2 | 4 | 8 | Firebase security rules reviewed quarterly; no plain-text credential storage; MFA on all admin accounts; Sentry error monitoring (pending DPA); annual pen test planned post-Series A | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-014 | Operational | me-central2 GCP region experiences multi-day outage due to infrastructure failure or regional event in Dammam | 1 | 5 | 5 | BCP/DR Section 4.1; Firestore daily snapshots; CDN static fallback for library; GCP SLA monitoring; evaluate off-region read replica post-Series A | 1 | 4 | 4 | Founder | Monitoring | May 2026 | May 2027
RR-015 | Strategic | Series A not raised by Sep 2027, forcing bridge extension or down-round at unfavourable terms | 2 | 4 | 8 | Maintain investor update cadence from Month 1; build data room early; hit OKR milestones as proof points; maintain ≥18mo runway so negotiation is never forced; engage 3+ VCs in parallel | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-016 | Reputational | Negative press or social media event (e.g. cadet fails exam citing Captain Adel error) damages brand before scale | 2 | 4 | 8 | Comprehensive disclaimer on all AI answers; rapid response playbook in Marketing Crisis Comms doc; monitor social mentions weekly; never market as 'exam guarantee' | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-017 | Operational | Key early engineering hire departs within 6 months, creating knowledge gap in RAG pipeline | 2 | 4 | 8 | Document all system design decisions in Decision Log; code in Git with full commit history; 12-month cliff vesting; competitive comp benchmarked to market; knowledge transfer protocol before any departure | 2 | 3 | 6 | Founder | Open | May 2026 | May 2027
RR-018 | Financial | Gross margin falls below 70% due to Gemini API token cost growth as usage scales, compressing economics | 3 | 3 | 9 | Prompt caching; BM25 pre-filter reduces tokens sent to LLM; set per-session token budget; model cost tracked monthly vs revenue; pricing model includes API cost buffer | 2 | 2 | 4 | Founder | Open | May 2026 | May 2027
RR-019 | Strategic | Academy customer churns after pilot due to low cadet engagement (not product quality), creating negative reference | 3 | 3 | 9 | Cadet engagement tracked weekly during pilot; proactive CSM check-in at Day 30; identify and fix adoption blockers before Day 45; 60-day pilot standard gives time to course-correct | 2 | 2 | 4 | Founder | Open | May 2026 | May 2027
RR-020 | Regulatory | GACA updates exam syllabus or regulations mid-contract, making existing library content materially incorrect | 3 | 4 | 12 | Library ingestion pipeline with GACA update monitoring; alert system when new GACA publications detected; quarterly library audit against current GACA AIPs; notify academy admins of content updates | 2 | 2 | 4 | Founder | Open | May 2026 | May 2027
RR-021 | Cyber | Third-party supply chain attack via npm or Python dependency compromises Fly GACA application code | 2 | 3 | 6 | Dependabot / npm audit in CI pipeline; lock dependency versions; no untrusted packages; security review of all new dependencies; separate prod and dev credentials | 2 | 2 | 4 | Founder | Open | May 2026 | May 2027
RR-022 | Financial | Foreign exchange risk on any USD-denominated vendor contracts (Google, potential CDN) as SAR is pegged but invoice FX timing varies | 2 | 2 | 4 | Negotiate SAR-denominated contracts where possible; Google Cloud billed in USD — budget 5% FX buffer in financial model; review FX exposure quarterly with accountant | 1 | 2 | 2 | Founder | Monitoring | May 2026 | May 2027
RR-023 | Operational | GACA-published PDF documents change format or URL structure, breaking citation links in Captain Adel answers | 3 | 3 | 9 | Citation URL validation job runs weekly; broken link alert to engineering within 24hr; fallback to document title if URL broken; RAG eval includes citation validity check | 2 | 2 | 4 | Founder | Open | May 2026 | May 2027
RR-024 | Strategic | GCC expansion (UAE/Bahrain) delayed due to local regulatory requirements (GCAA approval, local entity needed), pushing ARR ramp | 2 | 3 | 6 | Map GCC regulatory requirements in Y1; engage local legal counsel in UAE by Q3 2026; design product to support multi-jurisdiction citation sets; KSA revenues de-risk GCC delay | 1 | 2 | 2 | Founder | Open | May 2026 | May 2027
RR-025 | Reputational | Investor or media discovery of AI training on copyrighted aviation materials without proper licence or attribution | 2 | 4 | 8 | Legal review of all training data sources; use only GACA-published open documents; RAG retrieval (not fine-tuning) avoids reproduction; Apache 2.0 licence on infrastructure; document all content sources | 1 | 3 | 3 | Founder | Monitoring | May 2026 | May 2027

## Heat Map
Fly GACA — Residual Risk Heat Map (Likelihood × Impact)
Likelihood \ Impact → | 1 — Negligible | 2 — Minor | 3 — Moderate | 4 — Major | 5 — Catastrophic
5 — Almost Certain | Score: 5 | Score: 10 | Score: 15 | Score: 20 | Score: 25
4 — Likely | Score: 4 | Score: 8 | Score: 12 | Score: 16 | Score: 20
3 — Possible | Score: 3 | Score: 6 | Score: 9 | Score: 12 | Score: 15
2 — Unlikely | Score: 2 | Score: 4 | Score: 6 | Score: 8 | Score: 10
1 — Rare | Score: 1 | Score: 2 | Score: 3 | Score: 4 | Score: 5
Legend:
High Risk (Score ≥ 15) — Immediate action required
Medium Risk (Score 9–14) — Active monitoring required
Low Risk (Score ≤ 8) — Routine monitoring

## Mitigation Tracker
Mitigation Action | Linked Risk IDs | Owner | Due Date | Status | Notes
Execute key-person life insurance policy (≥3M SAR) on Founder | RR-005 | Founder | 31 Jul 2026 | In Progress | Insurance broker shortlisted
Complete Commercial Registration (CR) via MISA | RR-009 | Founder | 30 Sep 2026 | In Progress | Balady agent engaged
Implement Gemini API prompt caching to reduce token spend ≥30% | RR-003, RR-018 | Engineering Lead | 31 Oct 2026 | Planned | Design doc in progress
Execute DPA with Sentry before activating error monitoring | RR-010, RR-013 | Founder + Legal | Before activation | Planned | Sentry DPA template received from legal
Onboard first technical hire with full production system documentation | RR-005, RR-017 | Founder | 31 Jan 2027 | Planned | JD drafted in HR pack
Conduct first annual DR drill simulating me-central2 outage | RR-014 | Engineering Lead | Q4 2026 | Planned | Drill scenario documented in BCP/DR plan
Legal review of all RAG training data sources for copyright compliance | RR-025 | Founder + Legal | 30 Sep 2026 | In Progress | GACA open publications confirmed; counsel reviewing edge cases
Select and DPA-execute transactional email provider (SendGrid or Postmark) | RR-010 | Founder | 30 Sep 2026 | Planned | Vendor shortlisting in progress
Set up weekly GACA publication monitoring and broken citation alert | RR-020, RR-023 | Engineering Lead | 31 Oct 2026 | Planned | Monitoring architecture designed
Conduct PDPL compliance review with external legal counsel | RR-010 | Founder + Legal | 31 Dec 2026 | Planned | Annual review cycle established
Benchmark HyperPay as Moyasar backup payment processor | RR-004 | Founder | 31 Mar 2027 | Planned | Evaluate API and Fatoora support
Engage UAE/Bahrain local legal counsel for GCC regulatory mapping | RR-024 | Founder | 30 Sep 2026 | Planned | Referral requested from KSA counsel
Build npm/Python dependency audit into CI/CD pipeline | RR-021 | Engineering Lead | 31 Oct 2026 | Planned | Dependabot configuration in progress
RAG citation URL validation job — weekly cron, broken link alert | RR-023 | Engineering Lead | 31 Oct 2026 | Planned | Spec written; not yet implemented
Achieve RAG eval pass rate ≥85% (from 71% baseline) | RR-006 | Engineering Lead | 31 Mar 2027 | In Progress | Tracked as Product OKR KR 2.1
Negotiate SAR-denominated billing with Google Cloud or add 5% FX budget buffer | RR-022 | Founder | 31 Dec 2026 | Planned | Reviewing Google Cloud billing options
Sign first academy on multi-year cohort contract to build reference and reduce churn risk | RR-019 | Founder | 31 Mar 2027 | In Progress | 1 academy in pilot stage
Launch investor update cadence (monthly) to build Series A pipeline | RR-015 | Founder | 01 Aug 2026 | Planned | Template drafted in Board Pack
Implement MFA on all admin Firebase/GCP console accounts | RR-013 | Founder | Immediately | Completed | MFA enforced on all admin accounts as of Apr 2026
Document all GACA relationship contacts in secure shared location | RR-005 | Founder | 30 Jun 2026 | In Progress | Contacts document in 11 Founder Ops folder