Digital Office Setup

Master 14-Day Checklist · Fly GACA · v1.0 · May 2026

Read this first: This is the day-by-day setup plan to stand up Fly GACA's digital office. Total time: 1-2 working days for the founder, plus async waits for DNS, vendor approvals, and verification. Total recurring cost: ~SAR 1,800/month for the founder-only stage; scales with team.

# Setup philosophy

- Pick the smallest tool that does the job today, not the one you'll need at 50 employees.

- Every tool must have an export path — never get locked in.

- Saudi-friendly first: tools that handle bilingual EN/AR, that bill in SAR or accept Mada, and that have clear PDPL data-residency stories where the data is sensitive.

- Single sign-on (SSO) via Google Workspace from day 1 — even with one user. Pays compounding interest as the team grows.

# Phase 1 — Domain, email, workspace (Day 1-2)

## Day 1 morning

- Confirm flygaca.com domain registration is current. Move DNS to Cloudflare (free tier) for faster propagation and DNS analytics.

- Sign up for Google Workspace Business Starter — SAR 25/user/month. Verify domain ownership via TXT record.

- Configure MX records pointing to Google. Wait 30 min for propagation.

- Create primary account: i@flygaca.com. Set up MFA (Google Authenticator + recovery code printed and stored physically).

## Day 1 afternoon

- Create the alias map (see Email Aliases Map document) — every alias your published documents reference must resolve to a real inbox or to founder.

- Set up Google Drive shared drive: Fly GACA. Apply the folder structure (see Drive Folder Structure document).

- Upload the entire Investor Package + Office Paperwork folders to Drive.

- Set up Google Calendar with founder's recurring meeting holds (see Calendar & Operating Rhythm document).

## Day 2 morning

- Set up Google Meet with i@ as primary host. Customize meeting room background with Falcon brand panel (optional).

- Configure Gmail signature for i@ + sales@ aliases (see Brand Asset Kit when built).

- Enable Google Drive desktop client on founder laptop. Set selective sync (no need to sync the entire Drive).

# Phase 2 — Collaboration & knowledge (Day 3-5)

## Day 3

- Create Notion workspace 'Fly GACA' with paid Plus plan (SAR 38/user/month). One user only for now.

- Mirror the Office Paperwork folder structure as Notion pages (top level).

- Migrate the Decision Log + Risk Register + Sub-Processor List + Vendor Register into Notion databases (these are operational and benefit from Notion's database features).

- Set up the Captain Adel persona Notion page as the source of truth for content voice + brand.

## Day 4

- Create Slack workspace flygaca.slack.com. Free plan is fine for now (10K message history).

- Configure channels per Slack Workspace Blueprint document.

- Connect Google Drive + Notion + Calendar to Slack.

- Add a Slack reminder bot for daily standup post in #standup at 10am KSA.

## Day 5

- Set up GitHub organization 'flygaca'. Move the existing flygaca repository to the org. Configure branch protection on main.

- Connect GitHub to Slack — push notifications to #engineering.

- Set up VS Code or Cursor with the Fly GACA workspace as the founder's daily editor.

# Phase 3 — Pipeline, ops & finance (Day 6-10)

## Day 6 — CRM

- Create HubSpot account (free tier — sufficient until ~1,000 contacts).

- Configure 2 pipelines: 'Academy Sales' and 'Investor Outreach' (see HubSpot CRM Configuration Guide).

- Import the Saudi Investor Target List as contacts.

- Connect HubSpot to Gmail (BCC integration) so investor + academy emails auto-log.

## Day 7 — Calendar & scheduling

- Sign up for Calendly Standard plan (SAR 38/month). Connect to Google Calendar.

- Create 3 booking links: 30-min academy demo, 30-min investor first-meeting, 60-min advisor call.

- Add booking links to Gmail signature, LinkedIn bio, X bio.

## Day 8 — Engineering ticketing

- Sign up for Linear (free for under 10 users). Set up Fly GACA team.

- Configure 3 cycles: Product · Content · Ops. Migrate any existing GitHub Issues.

- Connect Linear to Slack and GitHub.

## Day 9 — Security

- Sign up for 1Password Teams (SAR 75/month flat for first 10 users).

- Create vaults: Founder Personal, Company Shared, Engineering, Investor Materials, Customer Data.

- Migrate every credential from browser/scratch into 1Password.

- Enable hardware security key (YubiKey) for founder's primary Google account.

## Day 10 — Finance & accounting

- Open SME corporate bank account (Al Rajhi or SNB recommended for tech startups). See Banking & Treasury Policy.

- Sign up for Zoho Books or Qoyod for Saudi-friendly accounting (SAR 75-150/month). Configure Chart of Accounts (existing doc).

- Connect bank account + Moyasar to Zoho Books for auto-reconciliation.

# Phase 4 — Tracking, monitoring, automation (Day 11-14)

## Day 11

- Set up Google Analytics 4 + Plausible (privacy-friendly) on flygaca.com.

- Configure conversion events: signup, trial start, trial-to-paid, academy contact form.

- Build a one-page founder dashboard in Plausible (or Looker Studio) pulling MAU + conversion + paying users.

## Day 12

- Sign up for Sentry (error tracking — free tier ample for Year 1).

- Wire Sentry into the Captain Adel chat function and the SPA.

- Set up alerts: any production Sev1 error → SMS to founder + Slack #incidents.

## Day 13

- Sign up for Loom (Business plan — SAR 56/month). Used for academy demos, investor walkthroughs, async team comms.

- Sign up for Figma (Free for solo). Used for any future design work + brand asset edits.

## Day 14

- Set up Zapier or n8n for cross-tool automation (SAR 75/month). Initial automations: HubSpot deal won → Slack notification + Drive folder created; Gmail label 'investor' → HubSpot activity logged.

- Configure backup: Drive backed up to Cloudflare R2 (encrypted, weekly) — independent of Google.

- Final review: every credential in 1Password, every domain in DNS clean, every alias resolving, every recurring meeting on calendar.

# Recurring monthly cost (founder-only stage)

| Tool | Plan | Cost (SAR/mo) | Why this stage |
| --- | --- | --- | --- |
| Google Workspace | Business Starter, 1 user | 25 | Email + Drive + Calendar + Meet |
| Notion | Plus, 1 user | 38 | Knowledge wiki + databases |
| Slack | Free | 0 | Free tier sufficient for solo + first hires |
| HubSpot CRM | Free | 0 | Free tier sufficient under 1K contacts |
| Calendly | Standard | 38 | Booking links |
| Linear | Free | 0 | Free under 10 users |
| 1Password | Teams | 75 | Flat fee covers first 10 users |
| GitHub | Team | 20 | Private repos, branch protection |
| Zoho Books | Standard | 75 | Saudi-friendly accounting |
| Sentry | Developer | 0 | Free tier |
| Plausible Analytics | Growth | 75 | Privacy-friendly, GA4 alternative |
| Loom | Business | 56 | Async demos + team comms |
| Figma | Free | 0 | Solo founder tier |
| Zapier | Starter | 75 | Cross-tool automation |
| Cloudflare DNS | Free | 0 | Free tier sufficient |
| Backup (R2 storage) | Pay-as-you-go | 20 | Weekly Drive backup |
| TOTAL |  | ≈ SAR 500-600/mo | ≈ USD 130-160/mo |

# Recurring monthly cost (5-FTE team stage, projected month 12)

| Tool | Cost (SAR/mo) |
| --- | --- |
| Google Workspace × 6 | 150 |
| Notion × 6 | 225 |
| Slack Pro × 6 | 180 |
| HubSpot Sales Hub Starter | 75 (3 seats) |
| Calendly × 3 | 115 |
| Linear × 6 | 180 |
| 1Password Teams | 75 (still flat for ≤10) |
| GitHub Team × 6 | 120 |
| Zoho Books | 115 (Pro tier) |
| Sentry Team | 100 |
| Plausible | 115 |
| Loom × 3 | 170 |
| Figma × 3 | 185 |
| Zapier Pro | 150 |
| Bookkeeping outsource | 2,500 |
| TOTAL | ≈ SAR 4,500/mo (~ USD 1,200) |

# What to skip until Series A

- Salesforce — HubSpot Free does the job until you have a real revenue ops function.

- Snowflake / Databricks — Firestore + Plausible is enough until product analytics is the bottleneck.

- PagerDuty — Slack #incidents alert is enough until you have a 24/7 on-call rotation.

- Carta or Pulley — your simple cap table XLSX works until 5+ shareholders + ESOP grants > 5.

- Gusto/Justworks Saudi-equivalent — manual GOSI + payroll is fine until 4+ FTEs.

- Looker / Tableau — Plausible + Google Sheets covers founder-stage data viz.

# Saudi-specific notes

- Most SaaS vendors above bill in USD with foreign-card surcharge. Use Mada for SAR-billed where possible (Moyasar, Zoho local, Cloudflare via Saudi billing).

- Saudi work week is Sun-Thu. Configure Slack working hours, Calendly availability, and Google Calendar accordingly.

- Hijri calendar awareness: bake Hajj + Ramadan into recurring meeting cadence (see Calendar & Operating Rhythm).

- PDPL: any tool processing user personal data (HubSpot, email) needs a DPA review and goes into the Sub-Processor List.